|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NO | Task Name | WBS | Duration | 3 Sept – 15 Dec 2018 | Sept 2018 | | | | Okt 2018 | | | | Nov 2018 | | | | | Dec 2018 | | | |
| **1** | **2** | **3** | **4** | **1** | **2** | **3** | **4** | **1** | **2** | **3** | **4** | **5** | **1** | **2** | **3** | **4** |
| 1 | Main Project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Design | 1 | 8 week | 3 Sept – 3 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Main Page | 1.1 | 8 week | 3 Sept – 3 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Menu Bar | 1.1.1 | 1 week | 3 Sept – 9 Sept |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Search Bar | 1.1.2 | 2 week | 3 Sept – 16 Sept |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Control Interface | 1.1.3 | 6 week | 17 Sept – 1 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Login Form | 1.1.4 | 1 week | 9 Sept – 16 Sept |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 | New Account Form | 1.1.5 | 1 week | 9 Sept – 16 Sept |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 | Account Page | 1.2 | 6 week | 3 Sept – 14 Okt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 | Playlist Sidebar | 1.2.1 | 4 week | 17 Sept – 14 Okt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 | Code | 2 | 11 week | 17 Sept – 30 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 | Account Content | 2.2 | 5 week | 1 Nov – 30 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 | Account Setting | 2.2.1 | 3 week | 1 Nov – 19 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13 | Login | 2.2.2 | 3 week | 1 Nov – 19 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 | Session | 2.2.3 | 2 week | 11 Nov – 19 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15 | User Database | 2.2.4 | 3 week | 18 Nov – 30 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 16 | Control Content | 2.1 | 11 week | 17 Sept – 30 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17 | Player Seekbar | 2.1.1 | 4 week | 17 Sept – 14 Okt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18 | Player Interface | 2.1.2 | 2 week | 1 Okt – 14 Okt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 19 | Restore Saved Playlist | 2.1.3 | 4 week | 21 Okt – 24 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 20 | Volume | 2.1.4 | 4 week | 1 Nov – 25 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 21 | Playlist Array | 2.1.5 | 4 week | 7 Nov – 30 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 22 | Play Section | 2.1.6 | 5 week | 17 Sept – 21 Okt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 23 | Add Song Custom | 2.1.7 | 4 week | 7 Nov – 30 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 24 | Playback Control | 2.1.8 | 5 week | 24 Sept – 30 Okt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 25 | Search Content | 2.3 | 6 week | 17 Sept – 30 Okt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 26 | Search Engine | 2.3.1 | 5 week | 17 Sept – 25 Okt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 27 | Search Result Pagination | 2.3.2 | 5 week | 24 Sept – 30 Okt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 28 | Test | 3 | 16 week | 3 Sept – 14 Dec |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 29 | User Interface | 3.1 | 16 week | 3 Sept – 14 Dec |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 30 | Account Content | 3.2 | 8 week | 1 Nov – 14 Dec |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 31 | Control Content | 3.3 | 14 week | 17 Sept – 14 Dec |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 32 | Hosting | 4 | 1 week | 1 Dec – 7 Dec |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |